## Read Me
This spreadsheet was created by Synergy Professional Services, LLC (www.spspro.com). The structure and logic are © 2005-2009 by Synergy Professional Services, LLC, which licenses you to use, distribute and modify the spreadsheet at no charge as long as you retain this notice of authorship and copyright. Synergy does not provide any warrantees or support for this spreadsheet, but welcomes your comments and bug reports to info@spspro.com. Synergy also requests that if you make any cool improvements or fixes, please send a copy back under the same terms. Enjoy, and please visit the resources section of our website to check for updates and for other useful services and resources!
Click on the logo or steer your browser to www.spspro.com to visit the website.
Usage Notes:
This spreadsheet is an example of a simple dashboard for tracking multiple projects. A dashboard like this is often used by the management team to review the status of all projects in the organization and decide where to focus attention. Modify the columns to reflect the information that you want to track and report on for your projects, but keep the dashboard short and concise. Too much information can be overwhelming and make it hard to maintain.

## Instructions
Instructions for project managers on how to fill out this portfolio dashboard.
Update the projects for which you are the project manager. Many of the fields have drop down menus. Here is special explanation of some of the fields.
Current phase:
Use the project phases described in the Project Management Resource Kit. Usually projects that haven't entered the Define phase are not tracked on this dashboard, but if it is necessary to enter such a project, show its phase as "Concept". Similarly, if a completed project must be listed, show its phase as "Done".
Signoff dates:
The columns SO 1, SO 2, and SO 3 refer to the dates of the three required signoffs documented in the Project Lifecycle Resource Kit.
If the signoff is already complete, enter the actual date, followed by a "A" in the next column.
If the signoff is in the future, enter the date you are currently forecasting, followed by an "F" in the next column.
If you don't have enough information to even make an estimate of the signoff date, leave the field blank, as well as the next column.
Completion dates:
Project completion is defined as handoff complete, per the project management process documented in the Project Lifecycle Resource Kit.
In the "Approved at Signoff 2" column enter the completion date from the plan that was approved by your sponsor at SO 2. If your project has not reached SO 2 yet, leave it blank.
In the "Forecast / Actual" column, enter your current forecast of the project's completion date. It is understood that this forecast will be most accurate for projects in later phases. If the project is complete, enter the actual completion date.
Note: if you enter completion dates in both "Approved at Signoff 2" and "Forecast / Actual" columns, a R/Y/G indicator will appear next to the "Forecast / Actual" column indicating schedule health according to the slippage of the given dates. The thresholds are set on the data validation tab of this spreadsheet. They are currently:
G - forecasted completion is within 1 week of planned date
Y - forecasted completion is 1-2 weeks later than planned
R - forecasted completion is more than two weeks later than planned
Schedule Risk Indicator
Assess the risk of achieving the currently forecasted "Project Completion" date:
G - low risk, on track to hit forecast
Y - concerns, but recovery plan in place
R - issues, need help, high chance of missing forecast
Non-schedule Health Indicator
This indicator is for you to show the overall health of the project for aspects other than schedule. Enter R, Y, or G as defined here.
Considering other aspects of the project such as resources, participation, morale, and risk:
G - no significant concerns
Y - issues, but you have a recovery plan in place
R - issues, and your need help from sponsor
Comments / Recovery Action
If a project indicator is yellow, write a short comment describing your recovery plan. If an indicator is red, write a short comment describing what action you need from the directors. If your indicators are all green, your comments are optional.
Definitons:
Pre-initiate - approved but not started
Last Update: 10/26/09

## Dashboard
Project Portfolio
Focus of dashboard review meetings: What can we do to identify and resolve issues?
| Project Name | Current Phase | Depart-ment | Name of Project Manager | Name of Project Sponsor | Team Members | Signoff Dates | [5 empty] | Project Completion (Handoff Complete) Date |  |  | Health Indicators |  |  |  |  | Comments / Recovery Action | Last Update
[7 empty] | SO 1 |  | SO 2 |  | SO 3 |  | Approved at Signoff 2 | Forecast / Actual |  | Sched Risk | SR | SY | SG | Non-sched
| Example: Project Alpha | Execute | Dept 1 | John Doe | Kathy Frederich | T. Arnold, J. French, G. Merryman, N. Claseman, F. Friend | 2006-08-04 | A | 2006-09-15 | A | 2007-01-14 | F | 2007-02-01 | 2007-02-12 | Y | Y | 0 | 1 | 0 | G | Schedule recovery: will drop auto-update feature to save two weeks of coding and testing time. | 2006-10-16
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
| *** INSERT ABOVE THIS LINE *** | [20 empty] | format ver 070510
Last Update: 10/26/09

## Open Action Items
Open Issues and Action Items
ID | Issue Description | Action and Status | Entry Date | Owner | Due Date

## Closed Action Items
Closed Issues and Action Items
ID | Issue Description | Action and Status | Entry Date | Owner | Due Date

## Decision Log
Decision Log
ID | Action and Status | Entry Date

## Data Validation
Do Not Edit these entries unless you are the administrator of this spreadsheet.
These values determine when the Handoff Complete warning indicator lights
8 | <- | Yellow Threshold (Days Behind)
14 | <- | Red Threshold (Days Behind)
2000-01-01 | <- | Earliest date allowed by validation formulas
2016-12-31 | <- | Latest date allowed by validation formulas
Below are the lists that are used in data validation formulas. The formulas use a defined label that refers to the appropropriate range highlighted in yellow.
Phases |  | Stoplight Colors | Unused | Date Types | Departments | Unused
Concept |  | R |  |  | MB
Define |  | Y |  | A | TSO
Plan |  | G |  | F | All
Execute
Close
Done