Project Development Workbook

# Introduction

Why invent new templates for your projects?  Synergy has tuned this collection of project templates based on the feedback of hundreds of students and clients.  We are happy to share them with you so that you can benefit, too.  They are a starting point for you to customize for your own special situations.  Don’t expect to use every form for every project; instead, think of this workbook as a cookbook with a selection of recipes that you can pick from and modify to suit your taste.  And if you come up with any improvements, please share them back by sending a copy to Synergy for future editions of this workbook.

Synergy Professional Services

11330 SW Foothill Dr.

Portland, OR   97225

www.spspro.com

Table of Contents

Introduction	1

Simple Business Case	3

Causal Hierarchy	4

Project Charter	7

Notes on Chartering a Project	12

Stakeholder Identification	13

Stakeholder Management	14

Stakeholder Management Instructions	15

Project Kickoff Agenda	16

Project Kickoff Instructions	17

Team Charter	18

Responsibility Matrix	20

Instructions for Responsibility Matrix	21

Role Definition Worksheet	22

Boundaries and Escalation	23

Detailed Scope Definition Worksheet	24

Scope Definition Worksheet Instructions	26

Work Breakdown Instructions	27

Work Breakdown Structure Worksheet	30

Task Information Sheet	31

Task List	32

Instructions for Creating a Schedule	33

Network Diagram	37

Schedule Chart	38

Risk Assessment PI Matrix	39

Risk Management Action Plans	40

Risk Management Instructions	41

Meeting Agenda	43

Progress Report Template	44

Progress Report Instructions	45

Project Portfolio Dashboard	46

Dashboard Instructions	46

Issue and Action Item List Instructions	49

Change Request	50

Change Request Instructions	51

Instructions for Holding a Project Retrospective	52

Communication Needs Planning Form	57

Simple Business Case

(Use to decide whether to move an idea into the Define stage)

Opportunity Assessment

- Briefly describe the opportunity or need that you see.

Value to Customer

- List the top features required from the customer or user point of view.

- Briefly describe the major business benefits the customer or user will see.

Our Ability to Execute

- List the top development and adoption risks that may cause this project to fail.

- Estimate the delivery date and key milestones.

Fit

- Give a high-level estimate of investment required by period.

| Time period( |  |  |  |  |
| --- | --- | --- | --- | --- |
| Investment amount( | $ | $ | $ | $ |

- Give a high-level estimate of revenue or savings generated by period.

| Time period( |  |  |  |  |
| --- | --- | --- | --- | --- |
| Revenue amount( | $ | $ | $ | $ |

- Show payback period based on above estimates of investment and revenue:

- Describe how this proposal supports our strategy:

- Give your recommendation on how to proceed:

# Causal Hierarchy

How to Connect Projects to Strategic Objectives

Use this technique very early in a project, such as during chartering, to define clear links between the organization’s strategic objectives and what the project is expected to deliver. This technique helps the project team derive project deliverables from strategic objectives in a structured way, increasing the chances that a project will have the desired strategic impact.

## Causal Hierarchy

A causal hierarchy has three levels that are followed by an if / then test, as shown in the examples.  The test is especially useful for checking whether the logic of the project makes good sense.  Once you have a good causal hierarchy, created with discussion and buy-in from key stakeholders, finishing the charter is easy.

## Level 1: Strategic Goal

The level 1 section describes the “big picture” strategic intent, mission objective, or business objective that this project will help achieve, along with relevant measures of success and where the data for the measures will come from.

## Level 2: Purpose of Project

This section builds on level 1, describing the specific focus of the project that will enable it to contribute to achieving the organization’s strategic goals described at level 1.  The purpose listed here is the primary reason for the existence of the project.  (This project may be just a contributor to the strategic goals – other projects not listed here may be needed to fully achieve them).   The purpose listed here should clearly flow down from the goals and be at a greater level of specificity.  Success measurements for the purpose are clearly defined, along with data sources.

## Level 3: Deliverables

This section lists the major specific and tangible outputs (deliverables) that the project will create to accomplish the purpose described in the level 2 section. The deliverables are tangible, specific, measurable and clear.  They cover much of what would be needed to achieve the stated purpose.  Clear and specific success measures are stated for each deliverable, preferably with an indication of target timeline.

## Test

The three levels of a well-written causal hierarchy move from more general and strategic to specific and tactical as you go from top to bottom.  The hierarchy clearly explains what specific project deliverables are needed to provide a certain strategic contribution and why.  This is very valuable when you are defining a project and getting buy-in.  You can test whether your casual hierarchy does that by reading it from the bottom up as series of if-then statements.  It should read something like this:

- If the project delivers or produces <the specific things listed at level 3>, then it will achieve <the purposes listed at level 2>.

- If the project achieves that purpose, then it will have contributed to <the important goals listed at level 1> that the organization has.

## Summary

The example shows how a causal hierarchy helps you move from very general objectives (improve patient satisfaction) to specific and measurable project deliverables (design, pilot, and evaluate a way-finding process).  It can be challenging, because it forces you to think through specific and measurable cause and effect relationships that explicitly show how your project will deliver results with strategic impact.

A causal hierarchy does not replace the chartering process.  It is a useful complement, ensuring that the why and what sections of the charter document are well thought out.

# Project Charter

(Describes Why and What)

Project name:

Date of this charter:

One sentence description of project:

Strategic contribution

What strategic goal or desired future state will this project contribute to?

How and when will you measure the success of that strategic contribution?

Purpose of project

What specifically will this project focus on creating or improving? This should directly enable the strategic contribution described above.

How and when will you measure whether the project achieved that?

Investment

Estimate at a high level the investment that will be required (such as time, effort, money):

What current or potential work will we have to forego to make room for this project?

| Deliverables (What high-level tangible items or outputs will the project deliver?) SMART deliverables are Specific, Measurable, Actionable, Realistic and Time-bound. |
| --- |
| Description of deliverable | How and when will success of deliverable be measured? |
| Other information about deliverables: (if applicable) |
| Things we will not do (out of scope items): |

Key targets, constraints, and assumptions (for example, desired start and end date, cost targets, or anything that key stakeholders want the project team to use to guide the project.)

Major risks and opportunities to be managed

| Key roles, stakeholders, and decision-makers |
| --- |
| Role | Name / contact info | Major responsibilities |
| Project leader |  |  |
| Sponsor |  |  |

| Agreement to proceed to next phase |
| --- |
| Project leader |  |
| Sponsor |  |
| Funder |  |
| Other |  |

Instructions for Completing a Project Charter

## Purpose and Responsibilities

- This form is used during the define phase of a project to get initial alignment and agreement on why the project is being initiated and what it will produce.

- The sponsor and the project manager should work together to get this charter form filled out.  Involve as much of the core project team as possible to get their buy-in.

- The charter is not a replacement for a project plan.  Keep it at a higher level of detail; just detailed enough to make a decision at the next gate on whether it is worth investing in detailed planning for the project.

- The completed form should be about 3 pages long.  The entire define phase should be short, such as several weeks for many projects at a typical company.

- The charter is always subject to revision as the project progresses and the team and stakeholders learn more.  Changes should be discussed and agreed upon.  If the changes are significant, get the charter re-approved.

## Step-by-Step Instructions

### Short Description

Enter a brief description of the project so that other people can recognize it quickly.  This is just an identification tag, so don’t make it too fancy.

### Strategic Contribution, Purpose of Project, and Investment

In these sections, describe the why of the project.  Explain the business level costs and benefits that your company will get from this project.  Why is this project important and how does it link to your company’s business objectives?  This is a great place to use the causal hierarchy technique to create really clear linkages.

### Deliverables and Success Measures

In this section, describe the what of the project.

- What are the tangible deliverables that the project will deliver to its customers or users?

- How will you measure whether the project successfully delivered them?

- Use the SMART test.  Are the deliverables and success measures Specific, Measurable, Actionable, Realistic, and Time-bound?

- In the out of scope section write a short list of things that you don’t plan to deliver but that other people might be expecting, based on likely misunderstandings.

### Key Targets, Assumptions, and Constraints

Targets are order of magnitude estimates, since you are filling out this form during the define phase, before any detailed planning has been done for the project.  These are not commitments.  Also, document key assumptions and constraints that will shape the planning for this project.

### Major Risks and Opportunities

List major risks or opportunities that may significantly affect the success of this project.  Capture the big stuff here – don’t worry about minor items at this time.

### Major Roles

List the major project stakeholders and what role you expect them to have.  Make sure you include the project manager, the sponsor, and key team members (if known at this time).  This is not a laundry list.  List 3 – 8 stakeholders who are major internal or external customers of the project, decision-makers or contributors.  Key stakeholders are often people who do one or more of these things:

- Provide things to the project

- Pay for the work

- Do the work

- Support the results after the project is done (such as maintenance techs)

- Use the results of the project (such as line operators and sales people)

- Are an end customer

- Make major decisions that affect the project

- Can derail the project

### Approval of Charter

Formal approval is necessary to transition this project into the planning phase.  Get the signatures of the sponsor, project manager, and other especially key stakeholders so you are assured that they all agree on the direction that the project is taking.

# Notes on Chartering a Project

Although all stakeholders have a role in defining your project, the role of the sponsor is especially key.  The initial mission statement from your sponsor probably is missing information, creating a big opportunity for misunderstanding.  This happens frequently in the real world.  You will have to figure out what additional information you need and work with your sponsor to get it.  Too much ambiguity on project definition now could cause nasty misunderstandings later in the project.

Some things for you to think about:

- Should your project include some experimentation or research, for example if you have to determine the best technology or process to use?  If so, is that best handled as more than one project?

- Is your sponsor expecting you to deliver just a paper design, or is he expecting you to introduce it into wide usage?

- What things on the periphery of the project might you or the sponsor be missing?  For example, how much testing does he expect?  Will there be a pilot before full rollout?

- Will you be working with global counterparts on aspects of this project?  Are there skill set, location, or team aspects that will affect the definition of the project?

- What schedule and budget does your sponsor have it mind?  You won’t know until you do planning whether you can meet those expectations, but it would be good to know what your sponsor is thinking.  You may eventually have to reset his expectations.

The five major stakeholder roles on a project are listed below.  How should these stakeholders be involved in defining your project and writing the charter?

- Sponsor:  Champion of the project and the team.  Removes roadblocks to success.

- Management:  Line or functional managers.  They have long-term control over employees and resources.

- Customer:  Uses the result.  Often provides requirements and sometimes contributes funding.

- Project Team:  The people who will do the work.  Contribute time, skills, and effort.

- Project Leader:  The person who coordinates the project and drives it to completion.

# Stakeholder Identification

List the project stakeholders by name or group, along with a few words about what is most important to that stakeholder.

| Name of person, role, or group | What is important to them |
| --- | --- |

# Stakeholder Management

| High | Commitment |  |  | Desired |
| --- | --- | --- | --- | --- |
| Med |  |  |  |  |
| Low |  |  |  | Actual |
|  |  | Influence |
|  |  | Low | Med | High |

For the stakeholders that you consider most crucial to the success of the project, write a brief plan explaining how you plan to manage them over the life of the project.  To create your actions, consider:

- What are the stakeholder’s needs?  How will you meet those needs?

- What does the project need from the stakeholder?  How will you obtain it?

| Stakeholder name: |
| --- |
| Comments: |
| Action | Owner | Due Date |

| Stakeholder name: |
| --- |
| Comments: |
| Action | Owner | Due Date |

| Stakeholder name: |
| --- |
| Comments: |
| Action | Owner | Due Date |

# Stakeholder Management Instructions

## Step 1

List stakeholders using the Stakeholder Identification template.

## Step 2

Follow the steps below to create action plans showing how you will manage critical stakeholders over the life of the project.

- Mark the stakeholder’s current attitude toward the project on a commitment / influence matrix.  Then on the same matrix, mark where you need to them to be.  (You can type directly into the cells of the matrix, then drag the arrow to point in the correct direction.  See the example already typed into the matrix.)  Use this visual indicator to decide which stakeholders you are going to focus on, since you probably don’t have time to manage every stakeholder.

- For each high priority stakeholder, consider:

  - What are the stakeholder’s needs?  How will you meet those needs?

  - What does the project need from the stakeholder?  How will you obtain it?

Based on these considerations, list specific actions that will move the stakeholder from the current to the desired state.  If the stakeholder is already where you need him to be, list actions you will take to maintain this.

# Project Kickoff Agenda

| Project name: |  |
| --- | --- |
| Project number: |  |
| Project manager: |  |
| Sponsor name: |  |
| Date, time and location: |  |

| Topic | Facilitator |
| --- | --- |
| Welcome the project team and explain project’s purpose and connection to business objectives | Sponsor |
| Introduce project manager and team members. Discuss everyone’s role on the project. | PM |
| Walk through the charter so everyone understands it | PM |
| Walk through the planning steps that this project will follow. Agree on next steps. | PM |
| Agree on ground rules for how the team will work together. | PM |
| Working sessions, Q&A, and discussion, as appropriate |  |
| Celebrate! | PM |

Project Team Member Contact List

| Name | Department | Phone | Role |
| --- | --- | --- | --- |

# Project Kickoff Instructions

Purpose of a kickoff

The kickoff meeting gives a project a good, decisive start.  It is usually held early in the Plan phase, after the project’s charter has been approved and the project has passed its first stage gate.  Often more people join the project team at this time, as the project starts detailed planning.  The kickoff is a good way to get the new people aligned with the project and committed to reaching its goals.  You should also have some fun, creating an opportunity for everyone to get to know each other and build some enthusiasm for the project.

Who should attend?

- The sponsor

- The project manager

- The people that took the project through its Define phase

- New project team members, both core and extended

- Stakeholders

Tips

- The kickoff is an important event..  Prepare carefully.

- Make the kickoff a special event that stands out from the humdrum routine of meetings.   Use it to build enthusiasm.

- Plan activities that will build relationships and improve communication.  These don’t have to be “touchy – feely” types of activities.

- Which people are key to the success of the project?  Ensure that they attend.

- Allocate significant amounts of time to open discussion and working sessions.  Acknowledge concerns, get everyone’s questions answered, and make real progress on the new project.

- During the ground rules section of the agenda, identify the 3 – 5 things the team feels is most important about how they will work together.  Also use this time to agree on some housekeeping items, such as

  - A shared location for project documents

  - Where and when project team meetings will be held

- Try to block out external distractions so that everyone stays focused on the project.

- Ensure results of the kickoff are documented and followed up on.

# Team Charter

## Purposes

- Establish a framework for team interactions, agreed on by the team

- Set expectations and define “rules of engagement”

Instructions

As a team, decide what rules of engagement you will operate by for the duration of the program or project.

| Element | Rules of Engagement |
| --- | --- |
| Decision processes |  |
| Meeting management and frequency |  |
| E-mail usage |  |
| Information sharing and distribution (e.g. shared file area) |  |
| Conflict resolution |  |
| Crisis management |  |
| Feedback processes |  |
| Professionalism |  |
| Other |  |

## Blue Beard Team Charter Example

- We will all be on time for meetings, with a five-minute grace period.

- Any team member who is late or an unplanned “no-show” will pay a $2 penalty that will be given to the United Way.

- If we are unable to attend the meeting or will not arrive within the grace period, we will notify the meeting chair.

- If my schedule does not allow me to attend a meeting, I will send a capable person to act on my behalf or empower the team to make team decisions in that meeting without me.

- When sending e-mails to team members, the title will identify if it is an ACTION, NEEDS TO BE READ IMMEDIATELY, or INFORMATION ONLY.

- Team members agree to send only work-related e-mails to the entire team.

- Team members agree that if there is a conflict we cannot resolve internally, then that conflict will first be escalated to the program manager and then to the VP of operations.

- In the event of a crisis, the team leader and/or a designated backup for the team leader will contact everyone on the team with the latest crisis information and the team’s planned response, if any.

- The team members will give one another feedback on performance within two weeks of every major milestone or every two months in the absence of major milestones.

- The team will contact each other after normal working hours only in the case of an emergency.  (An “emergency” can be defined in the charter and may include project or operational issues at the team’s discretion.)

- The team agrees to treat everyone with respect at all times, will not yell or curse at one another, and will not speak negatively of others when they are not present.

# Responsibility Matrix

| Who ( What ( |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

R – responsible for, A – approve results, C – contribute to the work (help) , I – (must be) informed

# Instructions for Responsibility Matrix

Why?

Making program responsibilities clear within a matrixed organization can be hard, partly because of the complexity of the matrix.  A responsibility matrix can help this.

How?

To build a responsibility matrix, determine the level of detail for the activities you want to work with.  This may range from the work item level to the major responsibilities level, depending on what you are trying to accomplish.

Then list the activities, one per row.  Identify the stakeholders or groups who should be involved and list them, one per column.  Keep an eye out especially for activities or groups that have been confused or overlooked in the past.  It is OK, and sometimes preferable, to list groups instead of individuals in the columns.

Code the responsibilities into the matrix.  Watch for areas of possible misunderstanding, such as between groups or with outside organizations.  It is often useful to do this as a team, because the discussion brings a wider variety of perspectives and increases alignment.  You can define any code that makes sense to you and your team, but the RACI code is widely used.

R – responsible for

A – approve results

C – contribute to the work (help)

I – (must be) informed

Communicate the completed matrix and manage changes to it, even using change control if warranted by the impact.

# Role Definition Worksheet

Stakeholder Roles (Who will contribute to the project?)

| Name | Communication Channel & Freq. | Major Contribution or Involvement | Contact Info |
| --- | --- | --- | --- |
| Sponsors |
| Management |
| Customers |
| Project Team |
| Project Leader |
| Other |

The five major stakeholder roles on a project are:

- Sponsor:  Champion of the project and the team.  Removes roadblocks to success.

- Management:  Line or functional managers.  They have long-term control over employees and resources.

- Customer:  Uses the result.  Often provides requirements and sometimes contributes funding.

- Project Team:  The people who will do the work.  Contribute time, skills, and effort.

- Project Leader:  The person who coordinates the project and drives it to completion.

# Boundaries and Escalation

Specify who has authority for what (eg key decisions, approvals, or escalations)

Use escalation thresholds to define when to take action.  The example to the left shows two parameters that have thresholds, schedule variance and spending variance.  It also shows first and second level trigger thresholds.  The first threshold might trigger a warning to management, and the second might require immediate management intervention.

Diagram escalation thresholds for your project in the space below.

# Detailed Scope Definition Worksheet

Requirements

| ID | Requirement | Measures | Prio |
| --- | --- | --- | --- |
| Ex | System must allow real time reporting. | Response time to 95% of ad-hoc queries is less than 3 seconds. | A |

Priorities: A – required; B – highly desired; C – would be nice

Hint:  Can you trace each requirement back to a customer need or desire?

Other Considerations (Note other scope considerations and changes to charter here)

Key Project Stakeholders

| Name of Stakeholder | Title and Role on Project |
| --- | --- |

Project Team Members

| Name | Title and Function | % Available |
| --- | --- | --- |

Triple Constraint Priorities

(rank the top three)

Scope Management Approach (how will you manage future requests to change the scope?)

Approval

Project manager:

Funder:

Other:

# Scope Definition Worksheet Instructions

The deliverables of many projects are sufficiently defined in the project charter, which is written during the Define phase.  However, deliverables for other projects, primarily large or complex projects, must be defined in more detail before the project team can break down the work of the project into tasks to do.  If this is the case for your project, you can use this template to refine the scope into a list of requirements that defines in more detail the characteristics of what the project will produce.

How to fill out this form:

- Facilitate discussions among members of the project team to get an initial list of requirements.

- Balance the needs and desires of the users with the constraints and judgment of the project team.

- Be prepared to iterate though the list of requirements several times to refine it and get agreement.

- Try to cover the breadth of important aspects of what you will be creating, including reliability, standards compliance, performance, usability, and maintainability.

Tips for writing good requirements:

- A requirement describes a feature, function, or deliverable.  It describes what, not how.

- Requirements should have these characteristics:

  - Complete and consistent

  - Unambiguous

  - Specific

  - Verifiable

  - Feasible

  - Prioritized into categories such as required, highly desired, and would be nice (to give the project team guidance on where to make tradeoffs)

# Work Breakdown Instructions

The purpose of a Work Breakdown Structure (WBS) is to convert the description of the project's scope (the what) into a list of tasks that have to be done (the how).  Since this task list is the basis for further planning, it is important to get it right.  The WBS technique uses a methodical "divide and conquer" approach to help ensure that no tasks are overlooked.  Major advantages of creating a WBS are:

- it helps conquer complexity by breaking the entire project into smaller pieces that are easier to plan, execute, and monitor

- it helps you convert the what of the project that was your focus in the Define phase into the how to that is the focus of planning

- it does a good job at eliminating gaps and redundancies

It can be harder than it looks to build a good WBS, but the results are worth it.  Creating the WBS encourages orderly examination of the work that will be required to complete the project, creating a foundation for schedule, budget, and progress tracking.  Here is an example of a simple WBS.

## Steps for Creating a WBS

- The top level of a work breakdown structure is called level 0 and is always a single item that represents the scope of the entire project.  Sometimes level 0 is omitted for clarity, but it is always assumed to be there.

- Divide level 0 (the scope of the entire project) into approximately three to eight blocks of work.  This is the next level of the WBS and is called level 1.

- Continue breaking down each block into smaller blocks that go on the next lower (or indented) level.

- Label each block with a description of what work it includes, using a verb-noun form, such as "Define metallurgy tests."

## WBS Tips

- You should stop breaking down a branch when it meets the tests listed in the "When to Stop Breaking Down" section below.

- The WBS does not have to be symmetrical.  Some branches may have more levels than others have.

- Remember to include the work of managing the project in the WBS, such as "Communicate Status" or "Update Risk Plans."  For convenience, many writers show it as a separate branch of the WBS that begins on level 1.

- As you create the WBS, you can work from top to bottom, bottom to top, or any combination.  Pick a method that works well for your team and remember to use the sanity tests below to check the correctness of your WBS after you are done.

- Create the WBS as a team activity, possibly after you or a small team has sketched out the framework.  The cross-functional interaction identifies work and solves problems that might otherwise be overlooked.  It clarifies team roles and builds commitment.  A great way to do this is using stickies on flip charts or a whiteboard.

- Large WBS’s can be formatted as an indented outline rather than as a tree.

## When to Stop Breaking Down

Stop decomposing a branch of the tree when the work packages (lowest level tasks) in that branch are just small enough to be useful.  Useful is subjective, but here are some guidelines:

- It is estimatable.  It is small enough to estimate accurately.

- It is assignable.  You can reasonably assign this task to a person or small group with assurance that they will understand and complete it.

- It is trackable.  Typically, the length of time it will take to complete a work package should be from about 50% to 200% of the status reporting period that you plan to use during execution of the project.  This size task can be tracked accurately.  For example, if you plan to report progress on the project weekly, most of your work packages will typically be from 3 days to two weeks long.  Shorter work packages may be micromanaging, while you won’t be able to accurately measure progress on longer work packages.

Don't go smaller than necessary, but don't allow long, broadly defined tasks.  Applying these tests often results in work packages that are 1 - 2 weeks long.

## Sanity Tests for Your WBS

When you have completed the WBS, use these tests to verify that it is well-constructed.

- 100% Rule: Each child task is a subset of the summary task above it, and the complete set of child tasks adds up to the summary task.  Thus, the summary task merely summarizes the collection of children and becomes redundant once all children are specified.

- “Everything” Rule:  All work that will be done on the project must have a home somewhere in the WBS.  Remember to include the work of project management.

- “Activity -> Product” Rule: Every summary task and work package names an activity that produces a measureable result.  Avoid ambiguous and open ended activities.

- Work packages (lowest level tasks) are decomposed to an appropriate level of detail as described in a previous section.

# Work Breakdown Structure Worksheet

Draw or outline a Work Breakdown Structure (WBS) that converts your product scope (in the form of requirements from the scope definition) into the tasks that the project must complete.  Use “hierarchical decomposition” to eliminate gaps and redundancies.

List key milestones, making sure that they are SMART and linked to work packages from the WBS.

# Task Information Sheet

A project team can use this worksheet to gather detailed information about the tasks in their project.  The best time to use this form is generally after the team has created a WBS and is starting to work on creating a schedule and other detailed plans.

WBS ID and name of task

What will it deliver? (Activity -> Deliverable format)

Who will do it and at what level of effort? (list names, e.g. Fred Flintstone 50%; or skill sets, e.g. 2 CAD Engineers at 100%)

What else is needed to do it? From other groups Equipment and materials Special skills Special costs

What tasks come before and after it?

How long will it take? (optimistic, mostly likely, and pessimistic range)

Key assumptions

Risks

# Task List

| Project: | Quick Estimate: |
| --- | --- |
| WBS ID | Task | Predecessors | Resources | Duration |

# Instructions for Creating a Schedule

## Sequence the Tasks

- Gather up the collection of work packages from the WBS.  These are the tasks that must be done to complete the project.  (Summary tasks – the tasks with children – are not work packages.  Do not include summary tasks in the following steps because in a properly constructed WBS they are redundant with their children.)

- As a project team, decide the order in which the tasks will be done.

  - Write the short description of each task in verb-noun form on the top third of a sticky.  Include stickies for START and FINISH.  You may already have these stickies from the work breakdown that you did in the “Create tasks …” step.

  - Arrange the stickies in the sequence that will most effectively get the project done.  Draw arrows indicating the sequence.  Some projects will have a very simple sequence where almost all tasks must be done in serial order (the preceding task must be completed before the following task can begin).  Other projects may be able to speed things up by doing some tasks in parallel.  The example diagram shows that tasks B and C can be done in parallel once task A is completed. Task D can’t start until both B and C are done.

  - This diagram showing the sequence of tasks for a project is technically known as a network diagram.

## Estimate the Tasks

- Estimate how many working days and people each task will take.  Write this in the “Duration” and “People” sections of the sticky.  Then list other important resources that will be necessary to do the task, for example time on a piece of equipment or an expenditure of money.  The example shows that task C, “Research coolant options,” is expected to take 12 working days.  George will work on it approximately 50% of his time and an equipment technician (to be named later) 25% of her time.  Thus, the task will require a total of 9 person-days of effort, spread over 12 working days of time. The task will also require spending $2,000 for travel expenses to visit a potential supplier, as well as use of Lab 2, which is in very high demand.

- Insert milestones into the sequence of tasks.  Milestones have zero duration and zero effort.  They are valuable for several reasons:

  - They will help you monitor the project’s progress because you can see whether milestones are achieved on the date you planned for them.  This is called a tracking baseline.

  - They will help you communicate project status to other people.

  - They will become a synchronization point, both within and outside your project team.

  - They give people concrete intermediate goals to shoot for.

You should have a milestone for each key accomplishment or deliverable in your plan, as well as one for each gate in your project management process.  Generally, you should have one or more milestones every month.

## Create a Schedule Chart

- Determine the earliest dates that each task can be started and completed based on the information from the stickies and the network diagram.  Use the sequence information from the arrows in the network diagram to determine when a task can start, based on the finish dates of the tasks that immediately precede it.  Given the start date and the duration of a task as shown on its sticky, determine what its earliest finish date is.  Going from start to finish through the network diagram, do this for every sticky and enter the dates in the appropriate boxes.

- Create a schedule chart (also known as a Gantt chart) using the information on the stickies.  The schedule chart plots the tasks in your project against a timeline, so that people can easily see when things are supposed to happen.  Units of time are shown as columns.  Each row contains the information for one task, with a bar showing when the task is expected to occur.  Transcribe this information directly from the network diagram and stickies that you created in previous step.  As the example schedule chart below shows, you can also chart how people and resources on the project will be used over time.   This is the basis for a budget.

## Fix Conflicts

- Your schedule chart may show some problems.  In the example schedule chart, 125% of George’s time is allocated to the project during the first two weeks in December.  You may see problems such as

  - Over allocation of people or resources

  - Using a resource when it is not available

  - Milestones not achieved on target

  - Unacceptable cash flow

Fix these problems by modifying the schedule.  You may have to change the sequence of tasks, durations, assignments of people and resources, or other parts of your plan.

## Tips

- You can use software to assist with many of these steps.  Microsoft Project® supports all the above steps, but some people don’t have access to it.  Another option is to use the Excel spreadsheet template in the Resource Kit to automate most of the graphing work in step 6.

- See Eric Verzuh’s Fast Forward MBA in Project Management for more details on how to do good scheduling and estimating.

- Involve the project team in creating the schedule.  Get estimates and inputs from the people who are most familiar with the work that will be done.  One person may propose a first draft, for example of the task sequencing, but the project will get a better quality schedule as well as more enthusiastic commitment if you involve the people who will do the work.

- Understand the critical path of your schedule.  The critical path is the path or paths through the network diagram that have the longest duration, starting at the start node and ending at the finish node.  (It is good practice to have a single start node and a single finish node in the network diagram.)   The critical path reveals several important things:

  - The shortest length of time that the project can complete in, if everything goes according to the plan.

  - Tasks that you should focus the project team’s attention on.  Any task on the critical path that slips even a little bit will delay the end date of the entire project.  Conversely, a decrease in the duration of a task on the critical path will shorten the entire project.  Therefore, pay a lot of attention to critical path tasks!

- Related to critical path, the slack of a task is the amount of time that a task can be delayed without delaying the project’s finish date.  Tasks that are on the critical path have a slack of zero.  Non-zero slack usually means flexibility, because you can reallocate resources or priority from a task with slack to a task on the critical path, thereby reducing the total project length or preventing a critical task from slipping.   If most tasks in your schedule have zero slack, your schedule is probably risky.

# Network Diagram

Use this page to document the network diagram that you created using the instructions above.

# Schedule Chart

Use this template to draw the schedule chart described in step 5 of the instructions.

Risk Assessment PI Matrix

Project name:

Project manager:

Date:

## Identify and Prioritize Risks

Identify risks to the successful completion of your project.  Prioritize the risks by plotting each one on this Probability-Impact (PI) Matrix

# Risk Management Action Plans

Take action on the risks you’ve identified by creating proactive and contingency plans for the highest priority risks.

| ID | Risk Description (IF) | Impact Description (THEN) | P | I | Prio | Proactive Plan and Owner | Contingency Plan, Trigger and Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |

KEY	P: Probability	I:  Impact (H, M, or L from PI Matrix)	Prio:  Action Priority (Rank from 1 to 25 based on PI Matrix)

# Risk Management Instructions

The risk management process has four basic steps.

- Identify risks using “If / Then” format

- Analyze and prioritize risks

- Create and implement risk management plans

- Monitor risks and act when necessary

## Step 1 - Identify

Identifying risks is a team activity.  Use the charter to start the discussions on possible risks.  Don’t limit your questions to yourself or your project team.  Ask people who are not directly involved with the project, such as people outside your area of expertise.  For example, if you’re in engineering, talk to service, manufacturing, or marketing people.  You can also consult historical information such as postmortems and debriefs, as well as published information in books, articles, and case studies.

## Step 2 – Analyze and Prioritize

Now that you have a list of potential risks, prioritize it down to the top items that you and your team are going to focus on now.  Use a Probability-Impact (PI) Matrix like the one on the first page of this form (titled Risk Assessment PI Matrix) to drive the discussion.

A good way to use a PI matrix is for your team to meet as a group, write each risk on a sticky, and then place the stickies on a large copy of the matrix that you’ve drawn on flipchart paper. After placing the stickies, score each risk by multiplying the weights on the probability and impact axes for each cell.  For example, a high impact (weight = 5), medium probability (weight = 3) risk receives a score of 5x3 = 15.

If you prefer, you can type the risks directly into the Microsoft Word table cells on the form, rather than using a flipchart.  Whichever techniques you use, remember to write each risk in this format:  IF <something occurs>, THEN <impact>.

Put a high priority on managing the risks that get scores of 15 or higher.  Risks with low scores go on your watch list – don’t spend a lot of energy planning for them, but check them periodically.  For risks that score between 5 and 15, make a case-by-case decision on how much energy you will spend managing each one.

## Step 3 – Risk Management Plans

Use the Risk Management Action Plans worksheet on this form to create action plans for the high priority risks from the previous step.  Each risk management plan has two parts, with an owner responsible for implementing each part.

- In the proactive section, you decide on preventative actions that you will take now to reduce the probability that the risk will occur or to reduce the impact if it does occur.

- In the contingency section, you decide how you will react if the risk event occurs in spite of your proactive actions.  The trigger is the event that you will monitor to determine whether the proactive actions were good enough.  If the trigger occurs, you will implement the contingency plan.

Some classic risk management strategies are:

- Avoid - Eliminate a specific threat, usually by eliminating the cause, before the project enters the execution phase.

- Mitigate - Reduce risk by taking proactive actions to lower the probability of a risk event’s occurrence or to reduce its impact should it occur.

- Accept - Plan to accept the consequences of a risk (can be active or passive).

- Transfer – Move the burden of managing the risk to someone else who is better able to handle it (financially, expertise, or in other ways).

- Monitor – Defer action and monitor the risk.

## Step 4 – Monitor and Act

The owners of the proactive plans from the previous step should implement the preventative actions.  This may require help and support from other people, including managers and sponsors.  After all, great plans aren’t any good if you don’t execute them.  Likewise, contingency owners should monitor their risks and initiate the contingency plans when triggers occur.

Finally, risk management is not a one-time event.  Monitor and update your risk list and risk management plans regularly.  Look for new risks and risks that have changed substantially.  It is an excellent idea to devote a few minutes at every team meeting to a brief risk review.

# Meeting Agenda

Date: <date>, <start time> - <end time>

Location or call-in info:

Meeting purpose:  <short summary>

Specific objectives to be accomplished

Participants

| Name | Meeting Role | Contact Info |
| --- | --- | --- |

Outline of meeting

|  | Time | Topic | Who facilitates? | How long? | Purpose 2 |
| --- | --- | --- | --- | --- | --- |
| 1 | 9:00 | Greetings, review agenda and update open action items |  | 10 m | Update |
| 2 | 9:10 | Review risk landscape |  | 5 m | Discuss |
| 7 | 9:55 | End Review and log new decisions Review and log new action items (clear action description, owner and due date) Agree on next steps, meeting time & location |  | 5 m | Decide |

Attachments:

# Progress Report Template

| Project name: |  | Project Number: |  |
| --- | --- | --- | --- |
| Project manager: |  | Sponsor: |  |
| Date of this report: |  |  |  |

Overall Project Health

| Area | Health | Comment |
| --- | --- | --- |
| Budget | Y | This comment explains project team’s recovery plan |
| Schedule | R | This comment explains what help is needed from sponsor. |
| Scope | G |  |
| Overall | R |  |

Key to Project Health Indicators

Red:	Significant risk; need help from management or sponsor.  (Explain in comments.)

Yellow:	Issues, but recovery plan in place.  (Describe recovery plan in comments.)

Green:	OK (Comment is optional.)

Milestone Status

| Milestone | Dates | Health | Comments |
| --- | --- | --- | --- |
|  | Original Plan | Previous Report | Forecast / Actual |  |  |

Key to Milestone Health Indicators

Red:	Will significantly miss this milestone.  (Explain reasons and actions in comments.)

Yellow:	Issues, but recovery plan in place.  (Describe recovery plan in comments.)

Green:	Expect to hit this milestone.  (Comment is optional.)

Done:	Milestone is complete.  The date in the Forecast / Actual column is the actual completion date.

Current Cost Forecast for Total Project (update only on significant changes)

| Cost Type | Amount | Unit | Date Updated |
| --- | --- | --- | --- |
|  | Original Plan | Forecast / Actual |  |  |
| Capital |  |  | dollars |  |
| Expense |  |  | dollars |  |
| Labor |  |  | hours |  |

# Progress Report Instructions

- Update this report on a regular cycle, such as every two weeks.

- Header section:  Enter the identifying information for this project.

- Overall Project Health section:  Show your opinion of the project’s overall health in the areas of budget, schedule, and scope by entering the codes shown in the key below the table.  Enter explanatory comments if required.  The Overall indicator is the worst of the individual indicators.

- Milestone Status section:

  - Report about eight milestones in the table.  Always include milestones for the standard gate transitions in your Project Management Process, as well as a milestone for the completion of the project, even if some of these standard milestones are already completed.  (Indicate completed milestones by entering “Done” in the health field.)

  - The remaining milestones should be upcoming milestones in a rolling window from now to about 8 weeks into the future.  Drop completed milestones and add new ones as the project moves forward.

  - Enter three dates for each milestone.  In the Original Plan column, enter the milestone’s planned completion date from the approved project plan or (re-)baseline.  In the Previous Report field, cut and paste the date that you forecast for this milestone in your previous progress report.  In the Forecast / Actual column, enter your current best estimate of when the milestone will be (or actually was) completed.  If the milestone is already completed, also enter Done in the Health column, leaving the background color unchanged.

  - In the Health column, enter R, Y, or G and the matching background color to indicate the outlook for achieving the milestone on the planned date.  Use the health codes shown in the key at the bottom of the table.  Some health codes require an explanatory comment.  Enter the comment in the Comment column as explained in the key.

- Current Cost Forecast section:  Update this section whenever capital, expense or labor projections change significantly,

# Project Portfolio Dashboard

# Dashboard Instructions

The Dashboard gives managers and sponsors an overview of all projects on a single page.  It is not applicable to managing single projects – use it as part of an overall portfolio monitoring system.  Each project’s status is summarized on a single row.  Generally, each project manager updates the projects for which he is responsible, using information from his detailed project status reports.  The dashboard is updated on a regular cycle, such as every month before a standard portfolio review meeting.

This example assumes the “Define – Plan – Execute – Close” lifecycle for managing projects.  Change the dashboard to reflect your organization’s lifecycle.  Here is more information on specific columns:

Current phase

- Use the project phases from your organization’s project lifecycle, such as Define – Plan – Execute - Close.  Usually projects that haven't entered the first phase (Define) are not tracked on this dashboard, but if it is necessary to enter such a project, show its phase as "Not Started".  Similarly, if a completed project must be listed, show its phase as "Completed.”

Dates of Approvals

- The "Definition,” "Plan" and "Execution" columns refer to the dates of the first three required approval gates as documented in project management lifecycle.

- If the approval is already complete, enter the actual date, followed by an "A" in the next column.

- If the approval is in the future, enter the date you are currently forecasting, followed by an "F" in the next column.

- If you don't have enough information to even make an estimate of the signoff date, leave both columns blank.

Dates of Completion

- In the "From Approved Plan" column, enter the completion date from the most recent plan that has been formally approved by your sponsor.  This will either be the date from the plan approved at the completion of the Plan phase or the date from a more recent re-plan, if you have an approved re-plan.  If your project has not reached this point, leave it blank.

- In the "Forecast / Actual" column, enter your current forecast of the project's completion date.  This forecast date will be most accurate for projects in later phases.  If the project is complete, enter the actual completion date.

Health Indicators

- Enter your assessment of the health of the project with regards to budget, schedule and scope.   Set the corresponding indicator by typing R, Y, or G, using these definitions:

  - R(ed) - Significant risk; need help from management or sponsor.  (Explain in comments.)

  - Y(ellow) - Issues, but recovery plan in place.  (Describe recovery plan in comments.)

  - G(reen) - OK (Comment is optional.)

- The overall health indicator color is the worst of the individual colors.

Comments / Recovery Action

- If any project indicator is yellow, write a short comment describing your recovery plan.  If an indicator is red, write a short comment describing what action you need from the management team.  If your indicators are all green, your comments are optional.

Last Updated

Enter the date that you last modified or verified the information in this row.

Issue and Action Item List

| Project: | List owner: |
| --- | --- |
| ID | Issue Description | Action and Status | Entry Date | Owner | Due Date |
| ex | New textbook unavailable from the publisher | Select and order alternate text for fall term. As of 7/7/15, evaluating 3 new books | 6/25/15 | John S. | 8/10/15 |

# Issue and Action Item List Instructions

Try to prevent issues by using good risk management techniques.  However, prevention is not always possible.  Use this Issue and Action Item List to manage issues and action items that come up during the project.  Review this list frequently with the project team.  Especially make sure that each item has the name of owner who will take charge of it and a date for when the action is due.  That really helps focus the action.  If all else fails, take a “date for a date,” but never leave an action item without agreeing on an owner, next step, and due date.

When items are closed or no longer relevant, remove them from this list or transfer them to a separate section for inactive items so that the active items are not obscured by clutter.

Sometimes the team needs outside help to resolve issues.  Promptly escalate these issues to your sponsor, using the process below.  Don’t hesitate to escalate – it is usually better to escalate too quickly than it is to wait too long.  Escalation is a normal part of running projects in a busy environment, and one of the critical functions of a sponsor is to help you resolve issues.

# Change Request

| Project Change Request |
| --- |
| Project name: | Request ID: |
| Requested by: | Date of request: |
| Date decision needed: |  |
| Description |
| Description of requested change: |
| Business reason for change: |
| Type of change: ( Major (requires replanning effort) ( Minor | How much effort will be required to investigate this request? |
| Impact of Change |
| On project schedule: |
| On project cost: | Source of funding: |
| On features and functionality: |
| Other impacts: |
| Decision |
| Who will decide? |  |
| Description of decision and actions: |  |
| Authorizing signature: | Date of decision: |

# Change Request Instructions

Changes are inevitable and can actually be valuable.  They can provide:

- Business flexibility

- Technology improvements

- Learning from discovery

Be prepared to manage change in a constructive way.  Prohibiting change does not work, but uncontrolled change causes chaos, so you must strike a balance.  Judiciously allow changes, but make explicit decisions instead of just letting changes happen uncontrolled.  Understand the cost of each change (not necessarily in monetary terms) and its value to the project or business before make a decision.

Here are the basic components of a simple change control system.

- Have a starting baseline

- Submit change requests

- Investigate costs and benefits of proposed changes; look for better alternatives (this may be done by a people other than the submitter.)

- Make decision

- Communicate and implement changes

- Update the baseline

- Go back to step 2

Change control does not have to be complicated, slow, or high overhead.  You can scale it to meet the needs of your project.  However, it should always clearly define responsibilities and the steps that people should follow to make controlled changes to the project.

Sections on This Form

Use this Project Change Request form to handle changes in your project.  The form has three sections that you will fill out at different times.

- First, request a change to the project (step 2 above) by filling out the Description section of the form.

- Next, capture the results of the investigation (step 3 above) in the Impact of Change section.

- Finally, make a decision on the change request and record the results in the Decision part of the form.

# Instructions for Holding a Project Retrospective

## Purpose

Retrospective reviews help everyone in the organization benefit from the accumulated experience of many people.  Participants at a retrospective extract what they learned during the project, summarize it, and decide how to take action to improve future projects.  Retrospectives (also known as post mortems and lessons learned reviews) can make a huge difference in improving the performance of an organization over a relatively short number of projects.

All projects should hold at least retrospective, near its end.  For a long project, you may also want to hold small retrospectives periodically during the life of the project, rather than waiting until the end when people have forgotten the details of what happened earlier.   Hold small retrospectives at the completion of key milestones or phases of work.  Everyone’s memory will be fresh, and the organization can start benefiting from the lessons immediately rather than waiting until the end of the project.

Every project is a little different, so fine tune each retrospective to fit the specific goals, needs, and team dynamics of the group that will participate in it.   Typical goals of a retrospective include one or more of the following:

- Capture data on how much effort was required to do the project

- Get the story out about what the project did or did not accomplish

- Improve upon the process, procedures, management, and culture

- Capture collective wisdom

- Repair damage to the team by recharging people and giving them closure

- Enjoy the accomplishment!

## Steps

A good retrospective is a structured way to gather “lessons learned” from those who know best – people who worked directly on a project.  It looks backward at what happened in the past, and forward at what should be done to improve the future processes and skills of the organization.

All retrospectives are based on an unshakeable ground rule:  no blame allowed!  Norm Kerth, known as the grandfather of retrospectives, puts it this way:

Kerth’s Prime Directive

Regardless of what we discover, we must understand and truly believe that everyone did the best job he or she could, given what was known at the time, his or her skills and abilities, the resources available, and the situation at hand.

There are four primary steps to holding a retrospective:

Prepare: A retrospective session can go awry if the wrong participants attend, the agenda is por, or people are unprepared, especially when emotions run high.  Most retrospectives, even those about non-controversial projects, require careful preparation. In this step:

- Select participants.

- Find neutral facilitator

- Select subject areas

- Gather historical information about how the project went

Hold Retrospective Session:  Once you get past issues of safety, blaming, self-protection, and poor memory, the learning starts to happen.

- Gather highs and lows

- Determine root causes

- Repair damage

Analyze Results:  Quality expert Joseph Juran was famous for saying that the vital few must be separated from the trivial many.   That applies to a retrospective, too.  Most likely the retrospective session generated a long list of comments and ideas.  The full list may be overwhelming and thus unlikely to be acted on.  In this step, pick just the vital few to take action on.

- Summarize observations

- Make and prioritize recommendations

Act:   Too many retrospectives stop with a report that gets filed and never seen again.  That’s a pity.  The participants in the retrospective session will carry away some of the learning just by virtue of attending, but the real leverage of a retrospective comes when the organization agrees to change its tools, processes, and behaviors.  Therefore, the keepers of these tools, processes, and behaviors - often management - must act.

- Determine processes, tools, and behaviors to change

- Create action plans

- Manage the changes

## Who Should Participate

Key stakeholders should attend the retrospective.  But exactly who is that?   The project team, of course.  But don’t leave out representatives of internal customers, as well as other projects that were dependent on this project.   Often, they have different perspectives than the people who worked most closely on the project. Be sure to invite stakeholders who were unhappy because their observations may help avoid the unhappiness next time.   Managers who were closely involved with the project should generally participate, too.  The facilitator must make sure that participants feel safe enough to say what they really think even in the presence of people who are more senior.

If this results in a group that is too big to facilitate (upper limit of about 20 – 25 people, often fewer), consider holding hierarchical retrospectives.   Have sub-teams hold smaller retrospectives focused on a specific aspect of the project, then invite a representative from each sub-team to represent the sub-team’s findings at a summary retrospective.

## Preparing to Facilitate a Retrospective Session

Prepare a clear agenda in advance of the retrospective session so there is a good framework that will keep it on track.  Here are some agenda tips:

- Break the agenda into three major sections: establishing a safe environment, learning lessons, and recharging participants, and recommending changes.

- Include frequent breaks.  People will not be at their best if they are thinking about their next break rather than engaging in the discussion.

- Don’t over-structure the agenda.  Things will change, so leave enough time to allow the discussion to veer into unexpected but promising areas.

Unearth real historical data before the session, too.  Some events in the project probably happened so long ago that memories are cloudy.  Consider collecting the following kinds of information so that the session is based on facts:

- Effort data – how much work was invested in the project

- Performance and baseline information – how the project met objectives for schedule, budget, quality, and scope or features compared to the original plan or forecast

- Risk information – what risks were identified and acted on?  What risks happened?

You can even turn this data gathering into a contest, awarding prizes to people who bring to the session the most artifacts, the most unusual artifact, and the most significant artifact.  Although a contest may seem silly, there are several benefits based on adult learning theory (Project Retrospectives: A Handbook for Team Reviews, Norman L. Kerth, p.120):

- An effective and fun way to stimulate important memories about the entire project

- Encourage thinking about the project in creative ways that develop meaningful stories

- Encourage people to think about what was most important during the project

- Ease people into reviewing the project

- Arouse curiosity, which is key to learning

## Holding the Retrospective Meeting

With the prework done, you are ready to hold the retrospective session. Here is an approach that works for many projects.

### Beginning of session

Goal: build a good foundation

- Establish an environment of safety and engagement.  Most participants must feel safe expressing their true observations.

- As a group, reconstruct the history of the project by creating a timeline that shows significant events.  This will help tickle memories.

### Middle of session

Goal: Discover lessons

- List the things that did and did not go well during the project.

- Understand the root causes and learn from these events.

### End of session

Goal:  Set the stage for action on the vital few

- Identify the highest priority learnings.

- Recommend actions that will affect skills, tools, processes, and behaviors.

Asking what did and did not go well opens up a lot of territory for most large projects.  It helps to have a framework that will focus the group's attention on things that are likely to be important, as well as help them not miss key areas.  Consider asking the group to focus on some of the topics in this list:

- Definition of the product or research - including scope changes and feature creep

- Planning

- Interaction with partners

- Quality and completeness of final product

- Technical – including design process, architecture, and tools

- Schedule, budget, and staffing levels

- People and teams - including skills, training, and morale

- Risk management

- Communication - within teams, between teams, and with other parts of the organization and its partners

- Subcontractor management

- Organizational interaction – organizational support, interaction with higher management, handoffs, and integration with other teams

- Project management methods

## Act on the Learning

At this point in the retrospective session, lots of data and observations have been collected.  Here is an example format for recording them.

| Topic | Issue | Suggestions for implementing next time |
| --- | --- | --- |

This is good material to archive, but in raw form the sheer volume will overwhelm busy readers who did not attend the session.  To increase the chances that the lessons will be acted on, select the vital few that are most important to act on.  Summarize them and create recommendations for action plans. Recommendations should aim for long-term improvements in one or more of these areas:

  - Individual and team skills

  - Processes and tools

  - Organizational behaviors

Keep the final report short so people will read it and remember what it says.  It also doesn’t hurt to archive the backup data you collected, including effort data and performance vs. actual comparisons.

Don’t just assume that the changes you recommend will happen when you publish the retrospective report.  Establish the importance of making the change, build a steering team to keep pushing on its implementation, and arrange quick victories.

## Tips

- Just do it!  Retrospectives are extremely effective and are an excellent investment of your time.

- Create an environment that is non-threatening, constructive and facilitated by an unbiased person.  The purpose is learning, not blaming.  Focus on what you can do in the future.

- Include input from a broad spectrum of team members and stakeholders who have a variety of views.  Include the people who will have to support or carry forward the results of your project.

- Cover both technical and non-technical areas of the project.

- Ensure that actions are prioritized, communicated, and followed up.

- Consider holding several small retrospectives throughout the project, such as at completion of key milestones or phases of work, rather than one big one at the end.  Everyone’s memory will be fresh, and your organization can start benefiting immediately rather than waiting until the end of the project.

# Communication Needs Planning Form

| Stakeholder | What do they need to know and when? | Their Current Awareness Level | Their Current Support Level | Criticality | Level of Communi-cation Effort | Method, Frequency, and Type | Who? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Loan officers | User features of client management system, status of key implementation milestones, dates for their training and pilots (and changes to any of the above) – monthly, plus upon major changes | Low | Low | High – success requires their input and support | High | Monthly update in “Loan Sharks” newsletter (FW) Weekly briefing for rep team (FV) (2 senior loan officers and manager ofgGroup) All 3 loan officers participate in UI and biz process team meetings (IV) and send weekly written updates to their teams (IW) | Jon |

| Key to Types of Communications |
| --- |
| FW: Formal Written | FV: Formal Verbal | IW: Informal Written | IV: Informal Verbal |

# Footnotes

James T. Brown, The Handbook of Program Management, p. 163-164

# Text boxes

Version 200901

## Strategic Goal Example (Level 1)

Improve the volume and satisfaction of outpatients visiting the orthopedics clinic.

Success Measures:  Within 3 months of implementing improvements:

- Patient volume through the clinic increases by 5%.

- Satisfaction scores of patients visiting the clinic increase by 20%.

Verification (sources of data):

- Volume reports from EHR system.

- Results from satisfaction survey that is administered at the end of each patient visit.

Assumptions

- Volume and satisfaction are driven at least partly by the effectiveness of the check-in and way-finding processes.

## Purpose Example (Level 2)

Improve patient check in and way-finding to increase preparedness and decrease lost time.

Success Measures:

- All patients are prepared for their appointments. No clinician time is spent on things that could have been taken care of before or at check-in.

- No patients get lost or frustrated on the way to their appointments.

Verification (sources of data):

- Daily debrief of medical technicians to count how many patients were not prepared.

- Patient scores on way-finding questions on end-of-visit survey.

Assumptions

- Enough patients will complete the end-of-visit survey so that we have statistically valid data.

- The medical technicians will accurately remember how many unprepared patients they saw and will log the number at the end of the day.

- We have an accurate baseline for improvement using prior survey data.

## Deliverables Example (Level 3)

- Paper design of a new way-finding and check-in process.  Measures:

  - The new process provides patients a single, accurate, consistent, and direct way to check in to clinic.

  - New process ensures all sources of direction data (Epic/mychart, reminder calls, and scheduling interactions) are consistent.

Target completion: 3 months from project approval date.

- A completed pilot of the new process.  Measure: A pilot of the new process runs and gathers data for 3 months.

Target date: Data vs. baseline on patient satisfaction and preparedness is collected and analyzed within 4 months of starting the pilot.

- An analysis report on the effectiveness of the new process with recommendations for next steps.  Measure and target date: Report presented to steering team within 8 months of the approval of this project.

Assumptions:  project is approved before October 15.

## Example Test of the Causal Hierarchy

- If we design and implement a new check-in process (level 3 deliverables), then patient preparedness will increase and lost time will decrease (level 2 purpose).

- If patient preparedness increases and lost time decreases, then volume and satisfaction levels of outpatients visiting the orthopedics clinic will improve (level 1 goal).

From level 1 of the causal hierarchy

From level 2 of the causal hierarchy

From any level of the causal hierarchy

From level 3 of the causal hierarchy

Charter version 200806

Chain of command for __________________

Chain of command for __________________

Chain of command for __________________

Quality

Development Time

Features

Development Cost

People

Duration

Resources

Task Description

(VERB – NOUN form)

Start

Finish

Task B

Task D

Task C

Task A

- George 50%

- Equipment tech 25%

12 days

- $2000 travel

- Use of lab 2 50%

C. Research Coolant Options

- George 50%

- Equipment tech 25%

12 days

- $2000 travel

- Use of lab 2 50%

C. Research Coolant Options

Start 12/4/06

Finish 12/19/06

Low

1

Med

3

High

5

High

5

Med

3

Low

1

Impact

Probability

1. Agenda items in blue are standing topics for recurring meetings.

2. Typical purposes:

Inform:  inform attendees of something.  No input or decision needed.

Decide: make a decision on the topic.

Discuss:  get input or discussion, but don’t make a decision

Update: get status or updates

Prepare

Hold Retrospective Session

Analyze Results

Take Action