## Schedule
[17 empty] | 0 | [6 empty] | #VALUE!
[14 empty] | Date -> | [9 empty] | Date-> | 2016-09-15 | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30 | 2016-10-01 | 2016-10-02 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-08 | 2016-10-09 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-15 | 2016-10-16 | 2016-10-17 | 2016-10-18 | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-22 | 2016-10-23 | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-29 | 2016-10-30 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-05 | 2016-11-06 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-12 | 2016-11-13 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19 | 2016-11-20 | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25 | 2016-11-26 | 2016-11-27 | 2016-11-28 | 2016-11-29 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04 | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-10 | 2016-12-11 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-17 | 2016-12-18 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-24 | 2016-12-25 | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2016-12-31 | 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-15 | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-21 | 2017-01-22 | 2017-01-23 | 2017-01-24 | 2017-01-25 | 2017-01-26 | 2017-01-27 | 2017-01-28 | 2017-01-29 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-18 | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01 | 2017-04-02 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-19 | 2017-04-20 | 2017-04-21 | 2017-04-22 | 2017-04-23 | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 2017-04-28 | 2017-04-29 | 2017-04-30 | 2017-05-01 | 2017-05-02 | 2017-05-03
[14 empty] | Work Week -> | [9 empty] | Work week-> | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18
| Butch's Market | [23 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43 | [6 empty] | Week 44 | [6 empty] | Week 45 | [6 empty] | Week 46 | [6 empty] | Week 47 | [6 empty] | Week 48 | [6 empty] | Week 49 | [6 empty] | Week 50 | [6 empty] | Week 51 | [6 empty] | Week 52 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18
| Report Date: |  | 2026-07-29 | [21 empty] | 2016-09-15 | [6 empty] | 2016-09-22 | [6 empty] | 2016-09-29 | [6 empty] | 2016-10-06 | [6 empty] | 2016-10-13 | [6 empty] | 2016-10-20 | [6 empty] | 2016-10-27 | [6 empty] | 2016-11-03 | [6 empty] | 2016-11-10 | [6 empty] | 2016-11-17 | [6 empty] | 2016-11-24 | [6 empty] | 2016-12-01 | [6 empty] | 2016-12-08 | [6 empty] | 2016-12-15 | [6 empty] | 2016-12-22 | [6 empty] | 2016-12-29 | [6 empty] | 2017-01-05 | [6 empty] | 2017-01-12 | [6 empty] | 2017-01-19 | [6 empty] | 2017-01-26 | [6 empty] | 2017-02-02 | [6 empty] | 2017-02-09 | [6 empty] | 2017-02-16 | [6 empty] | 2017-02-23 | [6 empty] | 2017-03-02 | [6 empty] | 2017-03-09 | [6 empty] | 2017-03-16 | [6 empty] | 2017-03-23 | [6 empty] | 2017-03-30 | [6 empty] | 2017-04-06 | [6 empty] | 2017-04-13 | [6 empty] | 2017-04-20 | [6 empty] | 2017-04-27
Key | Percent Com-plete | ID | Task Name | Forced Earliest Start Date | Dur-ation | P1 | P2 | P3 | P4 | P5 | Who | Comment | Start Date | End Date | Calculated Start Date | Calculated End Date | Rounded Duration | EF of Forced Start | Earliest Finish of P1 | Earliest Finish of P2 | Earliest Finish of P3 | Earliest Finish of P4 | Earliest Finish of P5 | EV Date | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
S | 100% | S | Start | 2016-10-10 | 0 | [7 empty] | 2016-10-10 |  | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [5 empty] | 2016-10-07
1.1 | 100% | 1.1 | Evaluate existing cold storage |  | 1 | S |  |  |  |  | Jason |  | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 1 |  | 2016-10-07 |  |  |  |  | 2016-10-10
1.2 | 100% | 1.2 | Evaluate existing display units |  | 1 | S |  |  |  |  | Sam |  | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 1 |  | 2016-10-07 |  |  |  |  | 2016-10-10
1.3 | 100% | 1.3 | Review energy usage data |  | 2 | S |  |  |  |  | Loretta[25%] |  | 2016-10-10 | 2016-10-11 | 2016-10-10 | 2016-10-11 | 2 |  | 2016-10-07 |  |  |  |  | 2016-10-11
1.4 | 100% | 1.4 | Document the analysis |  | 2 | 1.1 | 1.2 | 1.3 |  |  | Loretta[50%] |  | 2016-10-12 | 2016-10-13 | 2016-10-12 | 2016-10-13 | 2 |  | 2016-10-10 | 2016-10-10 | 2016-10-11 |  |  | 2016-10-13
2.1 | 100% | 2.1 | Research available rebates |  | 1 | 1.4 |  |  |  |  | Sumiko[25%] |  | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 1 |  | 2016-10-13 |  |  |  |  | 2016-10-14
2.2 | 100% | 2.2 | Research suitable products |  | 1 | 1.4 |  |  |  |  | Sumiko[25%] |  | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 1 |  | 2016-10-13 |  |  |  |  | 2016-10-14
2.3 | 100% | 2.3 | Compile comparisons & selection guides |  | 2 | 2.2 |  |  |  |  | Sumiko[25%] |  | 2016-10-17 | 2016-10-18 | 2016-10-17 | 2016-10-18 | 2 |  | 2016-10-14 |  |  |  |  | 2016-10-18
2.4 | 100% | 2.4 | Publish report |  | 3 | 2.3 |  |  |  |  | Sumiko[25%] |  | 2016-10-19 | 2016-10-21 | 2016-10-19 | 2016-10-21 | 3 |  | 2016-10-18 |  |  |  |  | 2016-10-21
3.1 | 100% | 3.1 | Confirm product selection |  | 1 | 1.4 | 2.4 |  |  |  | Tanner[75%] |  | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 1 |  | 2016-10-13 | 2016-10-21 |  |  |  | 2016-10-24
M1 | 100% | M1 | Approved to Purchase |  | 0 | 3.1 | [6 empty] | 2016-10-24 |  | 2016-10-24 | 2016-10-24 | 0 |  | 2016-10-24 |  |  |  |  | 2016-10-24
3.2 | 100% | 3.2 | Order equipment |  | 3 | M1 |  |  |  |  | Tanner[75%] |  | 2016-10-25 | 2016-10-27 | 2016-10-25 | 2016-10-27 | 3 |  | 2016-10-24 |  |  |  |  | 2016-10-27
3.3 | 75% | 3.3 | Decide on control systems approach |  | 2 | 3.2 |  |  |  |  | Sam[50%] |  | 2016-10-28 | 2016-10-31 | 2016-10-28 | 2016-10-31 | 2 |  | 2016-10-27 |  |  |  |  | 2016-10-30
3.4 | 50% | 3.4 | Create drawings |  | 3 | 3.3 |  |  |  |  | Carlos[25%] |  | 2016-11-01 | 2016-11-03 | 2016-11-01 | 2016-11-03 | 3 |  | 2016-10-31 |  |  |  |  | 2016-11-01
3.5 | 25% | 3.5 | Compile install & construction instructions |  | 6 | 3.4 |  |  |  |  | Carlos[25%] |  | 2016-11-04 | 2016-11-11 | 2016-11-04 | 2016-11-11 | 6 |  | 2016-11-03 |  |  |  |  | 2016-11-05
3.6 |  | 3.6 | Get agreement to proceed |  | 4 | 3.5 |  |  |  |  | Sam[50%] |  | 2016-11-14 | 2016-11-17 | 2016-11-14 | 2016-11-17 | 4 |  | 2016-11-11 |  |  |  |  | 2016-11-13
M2 |  | M2 | Ready to Start Field Work |  | 0 | 4.1 | [6 empty] | 2016-11-21 |  | 2016-11-21 | 2016-11-21 | 0 |  | 2016-11-21 |  |  |  |  | 2016-11-20
4.1 | 100% | 4.1 | Confirm Contractor Selection |  | 2 | 3.6 |  |  |  |  | Tanner[15%] |  | 2016-11-18 | 2016-11-21 | 2016-11-18 | 2016-11-21 | 2 |  | 2016-11-17 |  |  |  |  | 2016-11-21
4.2.1 |  | 4.2.1 | Supervise wiring upgrade |  | 1 | M2 |  |  |  |  | Janet |  | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 1 |  | 2016-11-21 |  |  |  |  | 2016-11-21
4.2.2 |  | 4.2.2 | Supervise installation |  | 2 | M2 |  |  |  |  | LaShawn |  | 2016-11-22 | 2016-11-23 | 2016-11-22 | 2016-11-23 | 2 |  | 2016-11-21 |  |  |  |  | 2016-11-21
4.3.3 |  | 4.3.3 | Check operation of new units |  | 1 | 4.2.1 | 4.2.2 |  |  |  | LaShawn |  | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 1 |  | 2016-11-22 | 2016-11-23 |  |  |  | 2016-11-23
5.1 | 25% | 5.1 | Develop training plan |  | 5 | 3.6 | 4.3.3 |  |  |  | River[25%] |  | 2016-11-25 | 2016-12-01 | 2016-11-25 | 2016-12-01 | 5 |  | 2016-11-17 | 2016-11-24 |  |  |  | 2016-11-25
5.2 |  | 5.2 | Train pilot stores |  | 15 | 5.1 |  |  |  |  | River |  | 2016-12-02 | 2016-12-22 | 2016-12-02 | 2016-12-22 | 15 |  | 2016-12-01 |  |  |  |  | 2016-12-01
5.3 |  | 5.3 | Train the trainer for future stores |  | 2 | 5.1 |  |  |  |  | River |  | 2016-12-02 | 2016-12-05 | 2016-12-02 | 2016-12-05 | 2 |  | 2016-12-01 |  |  |  |  | 2016-12-01
6.1 | 25% | 6.1 | Review Butch's phase 2 plan |  | 2 | 3.6 |  |  |  |  | LaShawn[25%] |  | 2016-11-18 | 2016-11-21 | 2016-11-18 | 2016-11-21 | 2 |  | 2016-11-17 |  |  |  |  | 2016-11-18
6.2 |  | 6.2 | Ensure Farwest able to provide tech support |  | 1 | 3.6 |  |  |  |  | Tanner |  | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18 | 1 |  | 2016-11-17 |  |  |  |  | 2016-11-17
7 |  | 7 | Manage Project |  | 53 | S | [6 empty] | 2016-10-10 | 2016-12-21 | 2016-10-10 | 2016-12-21 | 53 |  | 2016-10-07 |  |  |  |  | 2016-10-09
E |  | E | End |  | 0 | 7 | 5.2 | 5.3 | 6.1 | 6.2 | Sam[10%] |  | 2016-12-22 |  | 2016-12-22 | 2016-12-22 | 0 |  | 2016-12-21 | 2016-12-22 | 2016-12-05 | 2016-11-21 | 2016-11-18 | 2016-12-21
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
[17 empty] | 0 | [6 empty] | #VALUE!
*** End of Table. Insert Above This Row ***
Template Version: 161118
Insert Row(s)
Delete Row(s)
Sort By ID
Sort By Start

## Instructions
Setting Up the Workbook for the First Time
This workbook uses unsigned macros, which must be able to run for the workbook to function correctly. Since macros can contain viruses, Excel allows you to set the security level you want for macros. If Excel macro security level set too high, Excel will refuse to run macros. This workbook will run correctly at a setting of "medium." This setting will ask your permission to enable macros whenever you open a workbook that contains unsigned macros. (You should only give permission for workbooks that you know came from a trusted source.) To set this option In Excel 2003, select Tools ¦ Options ¦ Security. Press the button on the lower right that says Macro Security ...., then select the Security Level tab. Select the radio button that corresponds to the security level you want. Click OK twice. If you use a different version of Excel, the sequence may be slightly different.
Verify that the Excel "Analysis ToolPack" is activated. Without it, the date computations will cause errors. Normally, this workbook will install it automatically if it is not already activated, but if necessary, you can activate it manually. The Analysis Toolpak is included in a standard Excel installation. To activate it, choose Tools ¦ Add-Ins. In the resulting dialog box, select the Analysis ToolPak option. If the Add-Ins menu item is grayed out, first unprotect the worksheet on the Tools ¦ Protection menu. The password is blank. Install the ToolPak, then reprotect the worksheet with a blank password.
Setting Up A New Project
Set up the timeline for the project on the "User Setup" Tab. Fill out the yellow cells with the date that the timeline will start and the number of days between points on the timeline. Excel can only display a limited number of timeline points. Enter a value of 1 for the number of days between points to display a timeline about 8 months long. For longer projects, enter a larger value.
Set up the holidays for the project on the "User Setup" Tab. The schedule calculations assume that no work happens on weekends or holidays, unless you explicitly set a forced start date on one of these days. By default, you can have up to 16 holidays. Enter their names in the pink area and their dates in the corresponding blue area. (For designers, you may change the number of allowed holidays by changing the range referred to by the name Holidays. Also make a corresponding change to the colored areas on the User Setup Tab.)
Enter the name of your project at the top of the Schedule sheet.
Set the start date of your project by entering a Start milestone or other starting activity in the first line of the schedule table. Make sure that the "Forced Earliest Start Date" column for this line is set to the starting date for your project.
About the Calculations
This spreadsheet looks at task dependencies, durations, forced earliest start dates, weekends and holidays to automatically calculate a schedule. The calculated dates are displayed, along with a colored bar chart that graphically shows the schedule. If you change one of these elements for a task, the change automatically ripples through the schedule. Force as few dates a possible, otherwise you are defeating the purpose of the spreadsheet. It's only moderately sophisticated, but is good enough for many projects and beats doing the calculations and graphing by hand. If you need more sophisticated capabilities, consider using a program like Microsoft Project.
Entering Tasks and Milestones
Enter each task in your schedule on a blank line in the schedule table (on the Schedule Tab). Wherever possible, link the tasks by showing their dependencies in the P1 - P5 predecessor fields. The spreadsheet will automatically compute the start and end dates of linked tasks. You can force a "start no earlier than" date by entering a date in the "Forced Earliest Start Date" column, but do this very sparingly because it overrides the automatic scheduling capabilities. Each column is described in more detail below.
Percent Complete: The Gantt chart will show green bars to indicate completed work and blue bars to indicated uncompleted work. You can enter a value of 0% to 100% in this column to indicate how much of the work of this task is done. Blank means 0%.
ID: This is a unique identifier for the task. The predecessor fields refer to this identifier. It can be any text. If you have a WBS, consider using the WBS ID for the task.
Task Name: This describes the task. Good practice is to use a verb-noun phrase; for example "Research Elasticity Properties"
Forced Earliest Start Date: A date in this field forces the task to start no earlier than the given date, although a predecessor can still make it start later. Use this field sparingly. It should usually be blank except for the start date of the project and for external dependencies.
Computed Start Date: This field is automatically computed. It shows the earliest date that the task can start, based on the completion dates of the predecessor tasks and the Forced Earliest Start Date, if any. It assumes that work starts at the beginning of the day.
Computed End Date: This field is automatically computed. It shows the earliest date that the task can finish, based on the start date of the and duration of the task. It assumes that the task's work finishes at the end of this day. The finish date can be he same as the start date if the task has a duration of zero or one day. In this case, the task starts at the beginning of the day and ends either at the beginning (zero duration) or end (duration of 1) of the same day.
Duration: This is the number of working days that the task will take. Weekends and holidays are not counted as working days. A duration of zero is legal - it indicates that this task is a milestone (takes no time). Durations of zero automatically turn the cell yellow.
P1 - P5: Enter the text IDs of predecessor tasks in these columns. It must exactly match the text in the ID column of the predecessor task.
Who: This is a text field that you can use to capture who will work on this task (or other comments). It is not currently used in any computations.
Deleting Tasks
You can delete a task either by deleting the contents of all of its user-entered fields, or but using the Delete Row(s) button at the top. To use the button, use the usual Excel actions to select the row(s) you want to remove, the click the button. You can't delete rows outside of the scheduel table.
Inserting New Lines
If you want to make more blank lines to enter more tasks, select the row(s) immediately below where you want the new lines to be inserted, then click the Insert Row(s) button at the top of the schedule table. This works just like the usual Excel insert rows action, except that you can only delete rows in the schedule table.
Sorting
You can sort the rows in the schedule table (and Gantt chart) by clicking one of the sort buttons at the top of the Schedule tab.
Modifying the Spreadsheet Structure
Many areas on the spreadsheet are protected to guard the conditional formatting and formulas that make it work. You should be able to do all normal scheduling tasks in this protected mode by using the action buttons at the topic of the schedule chart. If you feel you must modify the structure of the spreadsheet (for example, to edit some formatting) you can unprotect the spreadsheet on the Tools ¦ Protection menu. The password is blank. Be really careful, including reading the notes on the Design Notes tab, because you may break some names, ranges, formulas, macros or other not-so-obvious things. Reprotect the spreadsheet with a blank password when you are done.
Meaning of Colors
Green - the green portion of a task bar in the Gantt section shows work that has been completed.
Blue - the blue portion of a task bar in the Gantt section shows work that is planned but not completed.
Light blue - an entry in the Duration column that is highlighted in light blue indicates that the row is a milestone and has zero duration.
Violet - the violet vertical bar in the Gantt section shows the date of the report, which is today's date (formula =TODAY()) unless the user has replaced the computation above the schedule table.
Yellow - a start date highlighted in light yellow means that date has been overridden by the date in the Forced Earliest Start field.

## User Setup
Setup Parameters
Enter timeline start date -> | 2016-09-15
Computed work week of start date -> | 38 | <- this value is computed automatically
Enter days between points on timeline -> (pick smallest value that allows Gantt to fit on timeline) | 1 | <- yellow area to left is a defined range called Increment
List of Holidays | vvv The blue area below is a defined range called Holidays. If you insert or delete lines, make sure the defined range and the column C formulas are still correct.vvv
Thanksgiving Day | 2008-11-27 | Th
Friday After Thanksgiving | 2008-11-28 | Fr
Christmas Holiday | 2008-12-24 | We
Christmas Holiday | 2008-12-25 | Th
New Year's Day | 2009-01-01 | Th
President's Day | 2009-02-16 | Mo
Memorial Day | 2009-05-25 | Mo
Independence Day | 2009-07-03 | Fr
Labor Day | 2009-09-07 | Mo
Thanksgiving Day | 2009-11-26 | Th
Friday After Thanksgiving | 2009-11-27 | Fr
Christmas Holiday | 2009-12-24 | Th
Christmas Holiday | 2009-12-25 | Fr
New Year's Day | 2010-01-01 | Fr

## Design Notes
Version 1.19-SPS by Jeff Oltmann of Synergy Professional Services. Please see Author tab for information on how to distribute or improve this spreadsheet. Remember to update the date in the row below when you change the structure or design of the spreadsheet. This date is used to create the revision footer for the schedule table.
2016-11-18
Cautions
Spreadsheet assumes all times are in units of days. Durations should be in working days.
The cells in the bar graph area have conditional formatting. Be careful editing this area.
Note that the Database range must be defined so that the leftmost column is the task ID. Also there are some defined areas on the User Setup Tab.
Note that rows 1-3 and several columns on the Schedule Tab contain special computations, are hidden and should not be messed with unless the structure of the spreadsheet is changed. The lookup formulas and the macros contain hardcoded references to the locations of certain columns. If you change the column structure, you may have to change these too.
Row 1 contains template rows that are inserted by the insert macro. All columns must have all of the most up to date, correct formatting, formulas AND conditional formatting!
Future Improvements
add resources rollup
add display of critical path
fractional durations are just truncated - may be able to fix this
display of bars and milestones still has some messy corner cases when the increment is greater than 1
Completed improvements
"completed" checkbox (or pct complete) field turns bar or appropriate part of it a different color - DONE
add dependencies - DONE
add capability to list holidays - DONE
insert and delete rows - DONE
Improve display of bars when granularity of timeline is greater than one day - DONE
Add check to make sure that insertions are within schedule table area - DONE
Add sort by ID and sort by date buttons - DONE
Minor bug - milestones that are off the timeline grid are always displayed in blue, even if 100% complete - FIXED
10/25/07, version 1.12: Added check that addin is loaded so workdays function works
10/31/07, version 1.12: updated holidays for 2007-2008, added day of week indicator
11/15/07, version 1.13: "User setup" tab: fixed several incorrect dates for holidays. Clarified notes regarding editing holiday list.
1/30/08, version 1.14, added instructions for setting macro security level to medium
10/14/08, version 1.15, improved robustness of database lookup in case of spaces or special characters in task ID's. Added comment field. Added horizontal spacing between gantt bars. Added fifth precessor column.
10/26/08, version 1.16, some minor formatting improvements, fixed milestone bug introduced in 1.15, added logic to round up fractional durations to next whole day, updated holidays, changed EV date calculation to include weekends and holidays in calculations so it looks smoother even if technically less correct, fixed glitches in conditional formatting
10/29/08, version 1.17: improved some documentation
11/12/08, version 1.18: version 1.15's "horizontal spacing" improvement broke sort functions. Changed approach to use white borders on green and blue gantt bars rather than spacer rows. This avoids the limitations in Excel's sorting ability that caused the broken sorts in 1.15. Also re-added row and column headings, fixed incorrect column refs in sort macros, and set delete function to automatically insert a blank row if user deletes all rows.
11/20/08: version 1.19 - updated dates for Christmas 2009 and New Year 2010

## Author
This spreadsheet was created by Synergy Professional Services, LLC (www.spspro.com). The structure and logic are © 2005-2016 by Synergy Professional Services, LLC, which licenses you to use, distribute and modify the spreadsheet at no charge as long as you retain this notice of authorship and copyright. Synergy does not provide any support for this spreadsheet, but welcomes your comments and bug reports to info@spspro.com. Synergy also requests that if you make any cool improvements or fixes, please send a copy back under the same terms. Enjoy, and please visit the resources section of our website to check for updates and for other useful services and resources!
Click on the logo or steer your browser to www.spspro.com to visit the wesbite.